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Tentative List
Goal

This document presents Israel World Heritage Sites' status report:

1. Inscribed World Heritage Sites

 
 1.1 Sites in Nomination Process 

2. Feasibility  Studies of Sites on the  Tentative List

    2.1 Feasibility Studies of proposed Sites to the 

        Tentative List

3. Sites on the Tentative List

4.   Proposed Sites to The  Tentative List

5. Harmonization of sites on the Regional / International  Level

6. Special Projects

1. Inscribed World Heritage Sites
	Site Name
	Inscribed
	OUV
Criteria
	No.
	WHC1 decisions
	Follow-up/Monitoring
	Focal Point

	Acre
	Dec. 2001
	(ii) (v) (vi)
	1042
	*
	 Acre Economic Development Company
	Dudu Harari

Michal Sofer

	Masada
	Dec. 2001
	(iv) (vi)
	1040
	 
	Israel Nature and Parks Authority (INPA)
	Eitan Campbell

	White City of Tel Aviv 
	Jun. 2003
	(ii) (iv)
	1096
	 **
	Tel Aviv Municipality
	Yirmi Hoffman

	Biblical Tels
	Jul. 2005
	(ii) (iii) (iv) (vi)
	1108
	***
	INPA
	Shahar Issacharoff

	Incense Route
	Jul. 2005
	(iii) (v)
	1107
	****
	INPA
	Gilad Gabai

	Bahai Holy Places
	Jul. 2008
	(iii) (vi)
	1220
	
	Bahai Community
	Albert Lincoln 


 1follow up on  the WHCommittee Decisions

*Old City of Acre:

· Combine a management plan with a clear policy for improving the social and economic conditions of the community, in order to ensure that it is a living city.

**The White City of Tel Aviv;

· Include a management plan for preservation, in order to ensure effectiveness of preservation 

· Monitor development in the city in order to improve quality of supervision of changes in existing urban fabric

· Recommends proposing height limits in inscribed area and buffer zone

***Biblical Tels (Megiddo, Hazor, Beer Sheba);

· Consider adding biblical tels as part of a serial nomination.

****Incense Route - Desert Cities in the Negev (Haluza, Avdat, Shivta, Mamshit);
· Implement an archeological strategy for the entire route and for each site separately.

· Improve and upgrade managements and preservation plans of the sites

1.1 Sites in Process of  Nomination 

	Site Status


	Submission date to UNESCO
	#
	World Heritage Committee Session
	Heritage Center examination
	OUV Criteria
	Management

 plan
	Video 
	PR 

brocuher
	Evaluation by advisory organizations
	Comments

	
	
	
	
	Complete 
	Partial
	
	
	
	
	ICOMOS
	IUCN
	

	
	
	
	
	
	
	
	
	
	
	Israel
	Intl.
	Israel
	Intl.
	

	Makhteshim Country


	4/2000
	1041
	Dec, 01
	+
	
	(ii) (iii) (iv) (v) (vii) (viii)
	-
	-
	-
	-
	Mars 2001
	May 2005
	-
	deferred

	Bet She’an

	1/2004
	1120
	
	
	+
	(ii) (iv) (v) (vi)
	-
	-
	-
	-
	
	-
	-
	withheld

	  Dan Arch (Tel Dan 


	1/2005
1/2007
	1105
	
	+
	
	(iv) (vi)
	+ 
	-
	-
	-
	Sep 2005

Sep 2006
	
	
	border dispute

	The Hula

	1/2005
	1219
	July  , 06
	+
	
	(iv)
	+
	-
	 -
	-
	
	June 2005
	Nov 05
	deferred

	Jerusalem Old City
	4/2000
	C148
	
	
	
	(i) (ii) (iii) (iv) (v) vi)
	 -
	-
	-
	-
	-
	-
	-
	WH List

 in Danger

	Ancient Sites of Christianity in Galilee

 
	2/2008

1/2009
	1309
	
	 +
	
	(iii) (vi)
	 -
	-
	-
	8/07
	11/08

10/09
	-
	-
	Withdrawn

	Region of Caves and Hiding
	 1/2009
	1370
	
	+
	
	(iii) (vi)
	
	
	
	7/09
	10/10
	
	
	Withdrawn

	Carmel Pre-History caves
	1/2011
	1393
	
	+
	
	(iii) (v) (viii)
	
	
	
	10/10
	9/11
	
	9/11
	


2.  Feasibility Study of Sites on the  Tentative List

	Site Name
	Initiated by
	Interested Parties
	Feasibility Study

by
	Evaluation by Israel Advisory Organizations 
	OUV
	comments

	
	
	
	
	ICOMOS
	IUCN
	
	

	White Mosque in Ramle
	Israel Government Tourism Corporation


	Ramle Municipality
	Israel Antiquities Authority
	-
	-
	(ii) (iv)
	

	Bet Shearim
	INPA
	INPA
	INPA
	5/11
	
	(i), (ii), (iii), (iv), (vi)
	INPA is reviewing  Icomos Israel comments


2.1.  Feasibility Study of Sites proposed to  the  Tentative List

	Site Name
	Initiated by
	Interested Parties
	Feasibility Study

by
	Evaluation by Israel Advisory Organizations 
	OUV
	comments

	
	
	
	
	ICOMOS
	IUCN
	
	

	Old City of Nazarat
	Local Municipality


	Local Municipality


	Local Municipality


	3/10
	-
	
	The city is reviewing Icomols Israel  comments


3. Sites on Tentative List

	Site Name
	Responsible Agency
	Interested Parties
	Potential Implementer
	Potential Sources of Financing
	OUV

	Early Synagogues in the Galilee
	Israel Antiquities Authority (IAA)
	IAA
	IAA
	
	(iii) (vi)

	Horvat Minnim
	Israel Nature and Parks Authority (INPA)
	INPA
	INPA
	
	(iv)

	Arbel (Nebe Shueb, Horns of Hittim)
	INPA
	INPA
	INPA / IAA
	
	(iii) (iv) (vi)

	Caesarea
	Caesarea Development Company
	CDC
	Caesarea Development Company
	
	(ii) (iv) (v) (vi)

	Pre-Historic Sites
	IAA
	IAA
	Regional Councils 
	
	(v)

	Mount Karkom
	Prof. E. Anati
	
	
	
	(iii) (v) (viii)

	Timna
	JNF and ITC
	Local community
	Regional Council
	
	)iii) (iv) (vii)

	Crusader Fortresses
	IAA
	IAA
	IAA
	
	(iv) (v) (vi)

	Degania and Nahalal
	Regional Council
	
	INPA
	
	(v) (vi)


4. Proposed Sites to The  Tentative List

	Site Name
	Proposed by
	Comments

	Old City of Beer Sheba
	Beer Sheba Municipality
	initial  meeting  

	Old City of Safed
	Safed Municipality 
	initial meeting  

	Nazareth*
	Nazareth Municipality
	Feasibility study was conducted 

	Gedera – Shack of the Biluim
	Gedera Local Council
	Correspondence

	Ein Kerem
	Ein Kerem Protection Committee
	initial meeting 

	Zippori (Sepphoris)
	Israel Nature and Parks Authority
	initial meeting

	Tiberias
	Tiberias Municipality
	First meeting  

	Biblical Tels – Arad, Gezer, Lachish
	INPA
	Extension of inscribed  sites

	Agricultural Terraces in the Judean Hills
	Jewish National Fund (JNF)
	initial meeting 

	Canyons of Judea Desert Ein Gedi – Ein Bokek
	INPA
	initial meeting  

	Old City and Port of Jaffa
	Jaffa Dev.Comp.
	

	Dor Port
	
	

	Limes of Rome Empire
	Israel World Heritage Committee
	(ii) (iii) (iv)


5. Harmonization of Sites on the Regional / International  

5.1 Culture Sites

	Site Name
	Potential Partners
	Nomination Statement
	Comments

	Biblical Tels
	Egypt, Iraq, Syria
	-
	Regional Coordination

	Crusader Fortresses
	Palestinian Authority, Syria, Jordan, Lebanon, Turkey
	-
	Coordination via France

	Umayyad Palaces
	Jordan, Syria, Palestinian Authority
	-
	Regional coordination

	Byzantine Monasteries in the Desert
	Greece, Jordan, Syria, Palestinian Authority
	-
	Coordination with M.E Countries

	Rock Art
	Jordan, Egypt
	-
	Coordination with Egypt

	limis of the Roman Empire
	Israel, Jordan, Syria
	-
	Coordination with Bratislava Group

	Ancient Port Cities of the Levant
	Turkey, Palestinian Authority, Egypt, Lebanon, Syria
	-
	Regional Coordination


5.2 Cultural Routes

	Site Name
	Potential International Partners
	Nomination Statement  

	Via Maris


	Turkey , Lebanon, Syria, 
	-

	Ottoman Railroad Routes
	Turkey, Saudi Arabia, Syria, Egypt
	-

	Pilgrimages to Jerusalem and Mecca
	Saudia Arabia, , Jordan
	-

	Olive Route 
	Malta, Turkey, Spain, Greece
	


6. Special Projects

	Initiative
	Cooperation 
	Activity 
	Comments

	 Hula - The Great Rift Valley  

	World Heritage Center
	Expert meeting in Israel, 

Oct. 2002
	Recommendations and Expert Report submitted

	
	  African Countries
  
	Expert meeting in Kenya

 (April 2007)

Malawi (Nov. 2005)
	Strategy GRV adopted by WHC

	
	BLI, WCPA, IUCN-MED
	Promotion of Nomination. Statement (Nov. 2010)
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